## Sheet1
North Pennsmen Spring Show 2022
| Show Dates: | Friday, April 22, 2022 @ 7:30 PM
Saturday, April 23, 2022 @ 2:00 PM
| Show Location: | Souderton Mennonite Church |  | Afterglow: | Leddy's Pub, Lederach Golf Course (Harleysville)
|  | 105 West Chestnut Street, Souderton, PA 18964 |  |  | 8900 Clubhouse Drive, Lederach, PA 19438
http://www.lederachgolfclub.com
| Guest Chorus: | The Liberty Belles |  | Contact: | Sue Gaudio, F&B Manager
phone - 215-513-3034, ext 16
| Quartets: | Opus 4 | Pending Music Team qualification |  | email - sgaudio@lederachgolfclub.com
|  | TBD | Pending Music Team qualification |  | CONFIRMED WITH SUE ON 2/10. NEED TO PROVIDE FINAL HEADCOUNT NLT ONE WEEK PRIOR TO EVENT
|  | TBD | Pending Music Team qualification
|  | TBD | Pending Music Team qualification
Task # | Due Date | % Comp | Activity Description | Owner | Notes
1 | 2022-02-01 | 100% | Show Title, Theme for Poster / Program cover design | Anne, Ig | feedback sent to Ig - 2/8/2022
2 | 2022-02-08 |  | Script development | Anne
3 | 2022-02-08 | 100% | Design poster and business cards, order tickets | Ig | feedback sent to Ig - 2/8/2022
4 | 2022-02-08 | 97.5% | Confirm key role assignments / ownership: | Mike
4.1 |  | 100% | Ad / Patron sales - Ig |  | Ig confirmed 2/8
4.2 |  | 100% | Venue Rental Agreement - Al Anderton |  | Al confirmed 2/9
4.3 |  | 100% | Tickets - Gary Dukart |  | Gary confirmed 2/9
4.4 |  | 100% | Internet Tickets / Social Media Mktg - Paul Kriner (supported by Tom Newmyer and Brian Quinn) |  | Tom and Paul confirmed 2/9 Paul will coordinate with Brian as needed
4.5 |  | 80% | Telephone Ticket Sales - Tom Newmyer |  | Will ask Tom N to cover as part of duties under Paul
4.6 |  | 100% | Pennettes - show day ticket sales, Will Call, ticket taking, COVID protocols, concessions - Joanne Anderson |  | Joanne confirmed 2/9
4.7 |  | 100% | Afterglow (Leddy's Pub) - Mike Challman |  | Sue Gaudio confirmed - event start 4/23/4:30 PM
4.8 |  | 100% | Non-NP Actor / Guest Artist honorarium (as appropriate) - Al Anderton |  | Al confirmed 2/9
5 | 2022-02-15 |  | Deadline for Quartets to express interest in Show slot | Anne
6 | 2022-02-15 |  | Ad / Patron sales package ready | Ig | feedback sent to Ig - 2/9/2022
7 | 2022-02-22 |  | Tasks 3 & 6 delivered to NP - Ad/Patron kickoff | Ig
8 | 2022-03-08 |  | Deadline for interested Quartets to audition for Music Team | Anne, Ig, Music Team
9 | 2022-04-03 |  | Final non-ad program copy delivered to Ig (Word format) | Mike
10 | 2022-04-09 |  | Last day for members to turn in ad/patron copy | Ig
11 | 2022-04-09 |  | Final ad/patron copy delivered to Ig | Members
12 | 2022-04-10 |  | Final program proofs ready for sign-off | Ig
13 | 2022-04-11 |  | Sign off on final proofs | Anne, Mike
14 | 2022-04-12 |  | Copy to printer | Ig
15 | 2022-04-21 |  | Pick up programs | Ig
16 | 2022-04-19 |  | Dress Rehearsal | Anne, Chorus
17 | 2022-04-22 |  | Friday Show - 7:30 PM | Anne, Chorus
18 | 2022-04-23 |  | Saturday Show - 2:00 PM | Anne, Chorus
19 | 2022-04-23 |  | Afterglow (following Saturday show) - Leddy's Pub, Ledarach Golf Course, Harleysville | Mike